## Summary
Sprint export — FRONTIER-FB2612 |  |  | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE
FRONTIER · 2026-06-03 → 2026-06-16 |  | NAME | 06/03 | 06/04 | 06/05 | 06/06 | 06/07 | 06/08 | 06/09 | 06/10 | 06/11 | 06/12 | 06/13 | 06/14 | 06/15 | 06/16
Archit Sugha
Sprint name | FRONTIER-FB2612 | Gajendra Singh Thakur | bar: THU to FRI
Total Sprint Capacity (h) | 512.00 | Harshitha K
Start date | 2026-06-03 | Mubarak Palagiri | bar: WED to FRI
End date | 2026-06-16 | Ramya Ure
Team | FRONTIER | Shyam Bhaskar Katuri | bar: THU
Sprint ID | 14 | Siddhant Mandal
Exported at | 2026-06-07 17:58 UTC
Stickies (count) | 28
Done stickies | 1
Open / not-done stickies | 27
Sum of estimates (h) | 402.00
Sum of Burnt hours (h) | 61.00
Planned capacity (sum estimates ÷ sprint capacity, %) | 78.5%
Free sprint capacity (sprint capacity − sum estimates, h) | 110.00
Stickies in column: do | 10
Stickies in column: doing | 17
Stickies in column: done | 1
Note on F4: PL — Planned leave · Full day · approved
Note on G4: PL — Planned leave · Full day · approved
Note on E6: PL — Planned leave · Full day · approved
Note on F6: PL — Planned leave · Full day · approved
Note on G6: PL — Planned leave · Full day · approved
Note on M8: PL — Planned leave · Full day · approved

## _chart_data (hidden)
Sprint export — chart backing (hidden)
Merged: Total sprint + members — est/burnt by kind (h)
Name | NDY burnt (h) | NDY est (h) | FSY burnt (h) | FSY est (h) | CODE burnt (h) | CODE est (h) | Improvement burnt (h) | Improvement est (h) | P&T burnt (h) | P&T est (h)
Total sprint | 0 | 0 | 60 | 399 | 1 | 3 | 0 | 0 | 0 | 0
Archit Sugha | 0 | 0 | 15.5 | 56 | 1 | 3 | 0 | 0 | 0 | 0
Gajendra Singh Thakur | 0 | 0 | 6 | 40 | 0 | 0 | 0 | 0 | 0 | 0
Harshitha K | 0 | 0 | 10.5 | 56 | 0 | 0 | 0 | 0 | 0 | 0
Mubarak Palagiri | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0
Ramya Ure | 0 | 0 | 3 | 61 | 0 | 0 | 0 | 0 | 0 | 0
Shyam Bhaskar Katuri | 0 | 0 | 14 | 64 | 0 | 0 | 0 | 0 | 0 | 0
Siddhant Mandal | 0 | 0 | 11 | 63 | 0 | 0 | 0 | 0 | 0 | 0

## SprintStatus
TEAM | Sticky ID | Title | Task type | Kanban | Owner | Estimate (h) | Burnt total (h) | Burn % | DoD (summary) | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16
FRONTIER | 34 | Cloud SMOKE | FSY | doing | Archit Sugha | 11 | 2 | 18.2 |  |  |  | 2
FRONTIER | 35 | Trex testing | FSY | do | Archit Sugha | 10 | 0 | 0
FRONTIER | 36 | Classical Smoke | FSY | doing | Archit Sugha | 8 | 2 | 25 |  |  |  | 2
FRONTIER | 37 | SGW Migration | FSY | done | Archit Sugha | 10 | 8 | 80 |  |  |  | 8
FRONTIER | 38 | CPI PSINT | FSY | doing | Archit Sugha | 12 | 1 | 8.3 |  |  |  | 1
FRONTIER | 39 | RCA Summary | FSY | doing | Archit Sugha | 5 | 2.5 | 50 |  |  |  | 2.5
FRONTIER | 75 | KT on AI | CODE | doing | Archit Sugha | 3 | 1 | 33.3 | vr |  |  | 1
FRONTIER | 63 | SGW Migration | FSY | do | Gajendra Singh Thakur | 10 | 0 | 0 | 2 VM migration in current sprint
FRONTIER | 64 | Tech Lead Support | FSY | doing | Gajendra Singh Thakur | 16 | 6 | 37.5 |  |  |  | 6
FRONTIER | 65 | Late office Support | FSY | do | Gajendra Singh Thakur | 14 | 0 | 0
FRONTIER | 40 | SGW Migration | FSY | doing | Harshitha K | 20 | 2.5 | 12.5 |  |  |  | 2.5
FRONTIER | 41 | Maintenance | FSY | doing | Harshitha K | 16 | 5 | 31.2 |  |  |  | 5
FRONTIER | 42 | OAM monitoring | FSY | doing | Harshitha K | 20 | 3 | 15 |  |  |  | 3
FRONTIER | 66 | Lab Support (FTP Migration- 2no.) | FSY | do | Mubarak Palagiri | 10 | 0 | 0 | Lab Support (FTP Migration- 2no.)
FRONTIER | 67 | 5G & SRAN QT | FSY | do | Mubarak Palagiri | 20 | 0 | 0
FRONTIER | 68 | Late office Support | FSY | do | Mubarak Palagiri | 14 | 0 | 0
FRONTIER | 69 | SGW Migration | FSY | do | Mubarak Palagiri | 15 | 0 | 0 | MIgration for debian 13 Sec GW-2VMs
FRONTIER | 70 | Late Office Support | FSY | do | Ramya Ure | 14 | 0 | 0
FRONTIER | 71 | SCM Infra Support | FSY | do | Ramya Ure | 12 | 0 | 0
FRONTIER | 72 | JAPCO Distcc Build work | FSY | do | Ramya Ure | 15 | 0 | 0
FRONTIER | 73 | JAPCO Coverity | FSY | doing | Ramya Ure | 15 | 2 | 13.3 |  |  |  | 2
FRONTIER | 74 | Docker Server updates | FSY | doing | Ramya Ure | 5 | 1 | 20 |  |  |  | 1
FRONTIER | 43 | Trunk Integration+MT | FSY | doing | Shyam Bhaskar Katuri | 28 | 9 | 32.1 |  |  |  | 9
FRONTIER | 44 | SGW Migration | FSY | doing | Shyam Bhaskar Katuri | 20 | 3 | 15 |  |  |  | 3
FRONTIER | 45 | Late Office Support | FSY | doing | Shyam Bhaskar Katuri | 16 | 2 | 12.5 |  |  |  | 2
FRONTIER | 46 | JAPCO | FSY | doing | Siddhant Mandal | 30 | 9 | 30 |  |  |  | 9
FRONTIER | 47 | Coverity | FSY | doing | Siddhant Mandal | 21 | 0 | 0
FRONTIER | 48 | Dev Support | FSY | doing | Siddhant Mandal | 12 | 2 | 16.7 |  |  |  | 2
Note on M2: +2.0h do→doing
Note on M4: +2.0h do→doing
Note on M5: +8.0h do→doing +0.0h doing→done
Note on M6: +1.0h do→doing
Note on M7: +2.5h do→doing
Note on M8: +1.0h do→doing
Note on M10: +6.0h do→doing
Note on M12: +2.5h do→doing
Note on M13: +5.0h do→doing
Note on M14: +3.0h do→doing
Note on M20: +0.0h doing→do
Note on M22: +2.0h do→doing
Note on M23: +1.0h do→doing
Note on M24: +9.0h do→doing
Note on M25: +3.0h do→doing
Note on M26: +2.0h do→doing
Note on M27: +9.0h do→doing
Note on M28: +0.0h do→doing
Note on M29: +2.0h do→doing

## Activity log
TEAM | Sticky ID | Sticky title | Owner | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16
FRONTIER | 34 | Cloud SMOKE | Archit Sugha |  |  | 2
FRONTIER | 35 | Trex testing | Archit Sugha
FRONTIER | 36 | Classical Smoke | Archit Sugha |  |  | 2
FRONTIER | 37 | SGW Migration | Archit Sugha |  |  | 8
FRONTIER | 38 | CPI PSINT | Archit Sugha |  |  | 1
FRONTIER | 39 | RCA Summary | Archit Sugha |  |  | 2.5
FRONTIER | 75 | KT on AI | Archit Sugha |  |  | 1
FRONTIER | 63 | SGW Migration | Gajendra Singh Thakur
FRONTIER | 64 | Tech Lead Support | Gajendra Singh Thakur |  |  | 6
FRONTIER | 65 | Late office Support | Gajendra Singh Thakur
FRONTIER | 40 | SGW Migration | Harshitha K |  |  | 2.5
FRONTIER | 41 | Maintenance | Harshitha K |  |  | 5
FRONTIER | 42 | OAM monitoring | Harshitha K |  |  | 3
FRONTIER | 66 | Lab Support (FTP Migration- 2no.) | Mubarak Palagiri
FRONTIER | 67 | 5G & SRAN QT | Mubarak Palagiri
FRONTIER | 68 | Late office Support | Mubarak Palagiri
FRONTIER | 69 | SGW Migration | Mubarak Palagiri
FRONTIER | 70 | Late Office Support | Ramya Ure
FRONTIER | 71 | SCM Infra Support | Ramya Ure
FRONTIER | 72 | JAPCO Distcc Build work | Ramya Ure
FRONTIER | 73 | JAPCO Coverity | Ramya Ure |  |  | 2
FRONTIER | 74 | Docker Server updates | Ramya Ure |  |  | 1
FRONTIER | 43 | Trunk Integration+MT | Shyam Bhaskar Katuri |  |  | 9
FRONTIER | 44 | SGW Migration | Shyam Bhaskar Katuri |  |  | 3
FRONTIER | 45 | Late Office Support | Shyam Bhaskar Katuri |  |  | 2
FRONTIER | 46 | JAPCO | Siddhant Mandal |  |  | 9
FRONTIER | 47 | Coverity | Siddhant Mandal
FRONTIER | 48 | Dev Support | Siddhant Mandal |  |  | 2
Note on G2: +2.0h do→doing
Note on G4: +2.0h do→doing
Note on G5: +8.0h do→doing +0.0h doing→done
Note on G6: +1.0h do→doing
Note on G7: +2.5h do→doing
Note on G8: +1.0h do→doing
Note on G10: +6.0h do→doing
Note on G12: +2.5h do→doing
Note on G13: +5.0h do→doing
Note on G14: +3.0h do→doing
Note on G20: +0.0h doing→do
Note on G22: +2.0h do→doing
Note on G23: +1.0h do→doing
Note on G24: +9.0h do→doing
Note on G25: +3.0h do→doing
Note on G26: +2.0h do→doing
Note on G27: +9.0h do→doing
Note on G28: +0.0h do→doing
Note on G29: +2.0h do→doing

## Daily tasks Details
Daily tasks Details — Sprint team view, stickies, and daily task records
Per-member sprint overview (same metrics as Sprint team page)
Team | Member | Sprint burnt % | NDY % burnt (by type) | FSY % burnt (by type) | CODE % burnt (by type) | NDY est (h) | NDY burnt (h) | FSY est (h) | FSY burnt (h) | CODE est (h) | CODE burnt (h) | Improvement % burnt (by type) | Process&Tools % burnt (by type) | Improvement est (h) | Improvement burnt (h) | Process&Tools est (h) | Process&Tools burnt (h) | Queue backlog (B) | Queue do (D) | Queue in progress (Dg) | Queue done (Dn) | Total est all stickies (h) | Total logged (h) | In progress titles (preview) | 06/03 | 06/04 | 06/05 | 06/06 | 06/07 | 06/08 | 06/09 | 06/10 | 06/11 | 06/12 | 06/13 | 06/14 | 06/15 | 06/16
FRONTIER | Archit Sugha | 28.0 | — | 27.7 | 33.3 | 0 | 0 | 56 | 15.5 | 3 | 1 | — | — | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 1 | 59 | 16.5 | Cloud SMOKE; Classical Smoke; CPI PSINT; RCA Summary | 0 | 0 | 16.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FRONTIER | Gajendra Singh Thakur | 15.0 | — | 15.0 | — | 0 | 0 | 40 | 6 | 0 | 0 | — | — | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 40 | 6 | Tech Lead Support | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FRONTIER | Harshitha K | 18.8 | — | 18.8 | — | 0 | 0 | 56 | 10.5 | 0 | 0 | — | — | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 56 | 10.5 | SGW Migration; Maintenance; OAM monitoring | 0 | 0 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FRONTIER | Mubarak Palagiri | 0.0 | — | 0.0 | — | 0 | 0 | 59 | 0 | 0 | 0 | — | — | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 59 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FRONTIER | Ramya Ure | 4.9 | — | 4.9 | — | 0 | 0 | 61 | 3 | 0 | 0 | — | — | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 61 | 3 | JAPCO Coverity; Docker Server updates | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FRONTIER | Shyam Bhaskar Katuri | 21.9 | — | 21.9 | — | 0 | 0 | 64 | 14 | 0 | 0 | — | — | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 64 | 14 | Trunk Integration+MT; SGW Migration; Late Office Support | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FRONTIER | Siddhant Mandal | 17.5 | — | 17.5 | — | 0 | 0 | 63 | 11 | 0 | 0 | — | — | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 63 | 11 | JAPCO; Coverity; Dev Support | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Every sticky — compact (no duplicate columns vs SprintStatus)
Team | Sticky ID | Title | Kanban | Est (h) | Burnt (h) | Burn %
FRONTIER | 34 | Cloud SMOKE | doing | 11 | 2 | 18.2
FRONTIER | 35 | Trex testing | do | 10 | 0 | 0
FRONTIER | 36 | Classical Smoke | doing | 8 | 2 | 25
FRONTIER | 37 | SGW Migration | done | 10 | 8 | 80
FRONTIER | 38 | CPI PSINT | doing | 12 | 1 | 8.3
FRONTIER | 39 | RCA Summary | doing | 5 | 2.5 | 50
FRONTIER | 75 | KT on AI | doing | 3 | 1 | 33.3
FRONTIER | 63 | SGW Migration | do | 10 | 0 | 0
FRONTIER | 64 | Tech Lead Support | doing | 16 | 6 | 37.5
FRONTIER | 65 | Late office Support | do | 14 | 0 | 0
FRONTIER | 40 | SGW Migration | doing | 20 | 2.5 | 12.5
FRONTIER | 41 | Maintenance | doing | 16 | 5 | 31.2
FRONTIER | 42 | OAM monitoring | doing | 20 | 3 | 15
FRONTIER | 66 | Lab Support (FTP Migration- 2no.) | do | 10 | 0 | 0
FRONTIER | 67 | 5G & SRAN QT | do | 20 | 0 | 0
FRONTIER | 68 | Late office Support | do | 14 | 0 | 0
FRONTIER | 69 | SGW Migration | do | 15 | 0 | 0
FRONTIER | 70 | Late Office Support | do | 14 | 0 | 0
FRONTIER | 71 | SCM Infra Support | do | 12 | 0 | 0
FRONTIER | 72 | JAPCO Distcc Build work | do | 15 | 0 | 0
FRONTIER | 73 | JAPCO Coverity | doing | 15 | 2 | 13.3
FRONTIER | 74 | Docker Server updates | doing | 5 | 1 | 20
FRONTIER | 43 | Trunk Integration+MT | doing | 28 | 9 | 32.1
FRONTIER | 44 | SGW Migration | doing | 20 | 3 | 15
FRONTIER | 45 | Late Office Support | doing | 16 | 2 | 12.5
FRONTIER | 46 | JAPCO | doing | 30 | 9 | 30
FRONTIER | 47 | Coverity | doing | 21 | 0 | 0
FRONTIER | 48 | Dev Support | doing | 12 | 2 | 16.7
Daily task rows (scrum_daily_task table)
Team | Row ID | Work date | Assignee | Title | Planned (h) | Committed (h) | Actual (h) | Status | Notes | Sort order | Linked sticky ID | Linked sticky title | Created at (timestamp) | Last updated (timestamp)

## Appriciation
Appriciation — one row per manager comment (author, comment, title, assignee)
Appriciation author | Appriciation comment | Title | Assignee
FRONTIER | very goo work | SGW Migration | Archit Sugha